## Task Tracker
Sr No. | Emp ID | Date | Task ID | Hours Spent | Remarks
1
1
1
| 1 | 19/10/2020 | 1 | 8 | completed
2
| 1 | 19/10/2020 | 2 | 8 | completed
| 1 | 17/10/2020 | 3 | 1 | completed
| 3 | 20/10/2020 | 4 | 3 | in progress
| 3 | 25/10/2020 | 4 | 6 | completed

## Task Data
Ticket Number | Task ID | Task Title | Task Description | Task Type | State | Priority | Assigned To | Efforts(In hours) | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Hours Spent | Hours Remaining | Extra Hours | Completed | Remaining | Estimate | Extra
T1 | 1 | Title 1 | Description 1 | Bug | COMPLETED | MEDIUM | 1 | 9 | 19/10/2020 | 19/10/2020 | 19/10/2020 | 19/10/2020
T1 | 2 | Title 2 | Description 2 | Feature | COMPLETED | MEDIUM | 1 | 9 | 19/10/2020 | 19/10/2020 | 19/10/2020 | 19/10/2020
T2 | 3 | Ttile 3 | desc 3 | Daily Task | COMPLETED | MEDIUM | 1 | 1 | 17/10/2020 | 17/10/2020 | 17/10/2020 | 17/10/2020
T567 | 4 | Title xyz | Desc xyz | Bug | COMPLETED | LOW | 3 | 4 | 20/10/2020 | 25/10/2020 | 20/10/2020 | 25/10/2020

## Employee Data
Employee Name | EmpID | UAID | Password | Admin Access
Anushree Kulkarni | 1 | 1 | Anu | Yes
Shashank Ramdohkar | 2 | 2 | Shashank | Yes
Smaily Bhatnagar | 3 | 3 | Smaily | No
Kevin Mathew | 4 | 4 | Kevin | No
Robert Downey | 5 | 5 | Robert | No
Scarlett Johansson | 6 | 6 | Scarlett | Yes